## Settings
Setting | Value
Path | C:\Users\t-ste\Documents\GitHub\2023-spring\adv-fe-tuth\tca-roll-for-it\
CSV Filename | tracking.csv

## Backlog Breakdown
Sum of delta | Dates
| Feb | Mar | Apr | May |  | Grand Total
Work Buckets |  |  |  | 2023-05-02 | 2023-05-04
getting-started
app-data-experiments | 1 |  | -1 |  |  | 0
choose-css-framework | 0 |  |  |  |  | 0
choose-js-framework | 0 |  |  |  |  | 0
create-project-and-repo | 0 |  |  |  |  | 0
first-github-pages-build | 0 |  |  |  |  | 0
tracking-spreadsheet | 0 |  |  |  |  | 0
misc
dynamic-navbar-title |  | 0 |  |  |  | 0
email-for-cloud-storage | 2.5 |  | -2.5 |  |  | 0
fork-and-publish | 0.5 |  |  |  | -0.5 | 0
light-and-dark-mode | 0.25 |  | -0.25 |  |  | 0
n-minus-one
game-over |  | 0.5 | -0.5 |  |  | 0
player-choice |  | 0 |  |  |  | 0
pwa-tweaks | 1 |  | -1 |  |  | 0
usability-tests-and-tweaks | 1 | -0.5 | -0.5 |  |  | 0
screens
general | 0 |  |  |  |  | 0
home-and-stats
avg-game-times | 0.5 | -0.5 |  |  |  | 0
game-list | 0.5 |  | -0.5 |  |  | 0
last-played | 0.5 |  | -0.5 |  |  | 0
leaderboard | 0 |  |  |  |  | 0
play-button | 0.5 | -0.5 |  |  |  | 0
returned-dice | 2 | -2 |  |  |  | 0
take-backs |  |  |  | 0 |  | 0
total-games | 0.25 |  | -0.25 |  |  | 0
ui-investigation | 1 | -1 |  |  |  | 0
winning-sequences | 1.5 |  | -1.5 |  |  | 0
play | 7 | -6.5 | -0.5 |  |  | 0
setup
add-new-player | 0 |  |  |  |  | 0
choose-from-existing-players | 0 |  |  |  |  | 0
start-game | 0.5 | -0.5 |  |  |  | 0
storage
cloud | 1.75 |  | -1.75 |  |  | 0
local | 1 |  | -1 |  |  | 0
Grand Total | 23.25 | -11 | -11.75 | 0 | -0.5 | 0