## Settings
Setting | Value
Path | C:\Users\t-ste\Documents\GitHub\2023-spring\adv-fe-tuth\tca-roll-for-it\
CSV Filename | tracking.csv

## Backlog Breakdown
Sum of delta | Dates
| Feb | Mar | Apr | May |  |  | Grand Total
Work Buckets |  |  |  | 2023-05-02 | 2023-05-04 | 2023-05-14
getting-started
app-data-experiments | 1 |  | -1 |  |  |  | 0
choose-css-framework | 0 | [5 empty] | 0
choose-js-framework | 0 | [5 empty] | 0
create-project-and-repo | 0 | [5 empty] | 0
first-github-pages-build | 0 | [5 empty] | 0
tracking-spreadsheet | 0 | [5 empty] | 0
misc
dynamic-navbar-title |  | 0 |  |  |  |  | 0
email-for-cloud-storage | 2.5 |  | -2.5 |  |  |  | 0
fork-and-publish | 0.5 |  |  |  | -0.5 |  | 0
light-and-dark-mode | 0.25 |  | -0.25 |  |  |  | 0
n-minus-one |  | 0.5 | -0.5 |  |  |  | 0
pwa-tweaks | 1 |  | -1 |  |  |  | 0
usability-tests-and-tweaks | 1 | -0.5 | -0.5 |  |  |  | 0
screens
general | 0 | [5 empty] | 0
home-and-stats | 6.75 | -4 | -2.75 | 0 |  | 2 | 2
play | 7 | -6.5 | -0.5 |  |  |  | 0
setup | 0.5 | -0.5 |  |  |  |  | 0
storage
cloud | 1.75 |  | -1.75 |  |  |  | 0
local | 1 |  | -1 |  |  |  | 0
Grand Total | 23.25 | -11 | -11.75 | 0 | -0.5 | 2 | 2

## Burn-up
date | release target rt | work completed rt
2023-02-07 | 30.25 | 0
2023-02-08 | 30.25 | 0.25
2023-02-09 | 30.25 | 1.25
2023-02-14 | 30.75 | 3.25
2023-02-17 | 32 | 5
2023-02-21 | 31 | 5.75
2023-02-22 | 31 | 5.75
2023-02-23 | 31 | 6
2023-02-24 | 31 | 6.5
2023-02-25 | 31 | 7.25
2023-02-28 | 31 | 7.75
2023-03-03 | 31 | 8.75
2023-03-04 | 31 | 9.5
2023-03-05 | 31 | 10.75
2023-03-07 | 31.25 | 12.75
2023-03-10 | 31.25 | 14
2023-03-11 | 31.5 | 14.25
2023-03-12 | 31.5 | 16.75
2023-03-13 | 32.25 | 17
2023-03-16 | 32.25 | 19
2023-03-22 | 32.25 | 19.5
2023-03-29 | 32.25 | 20
2023-04-03 | 31.75 | 23
2023-04-05 | 31.75 | 24.5
2023-04-06 | 31.75 | 25.75
2023-04-14 | 30.75 | 28.5
2023-04-19 | 30.75 | 30.25
2023-05-02 | 31.25 | 30.75
2023-05-04 | 31.25 | 31.25
2023-05-14 | 33.25 | 31.25